## Phase 1
Item | Output | Status | Status Notes | FINAL Due Date | Owner | Link
Overall | Write Phase 1 Overall PRD | Completed | Complete | 2025-09-20 | Bryanna / Leon | Athena Phase 1 PRD
Request Intake | Identify Mutual Customers | In Progress | Shared early list with Nidhi on 9/18 | 2025-09-18 | Bryanna | Link
| Identify Non-Mutual Customers | In Progress | Shared criteria with Athena week of 9/22 | 2025-09-22 | Bryanna
| Finalize Workflow | Completed |  | 2025-09-19 | Bryanna / Leon | Link
| Draft API Spec Review with Athena (Initial) | Completed | Presented on 9/25 | 2025-09-25 | Steve | athena_draft_create_request_schema
| Security Review | Completed | Scheduled to speak with Tyler on 9/29 | 2025-09-29 | Leon
| Finalize RequesterAPI PRD | Completed | Current PRD needs to be finalized | 2025-10-03 | Khristina / Steve | Requester API for Athena
| Draft API Spec Review with Athena (Followup) | In Progress |  | 2025-10-09
| End to End Workflow Review - All DV Teams | Not Started |  | 2025-10-17
| Share Finalized RequesterAPI Tech Spec | Completed |  | 2025-10-24 | Steve
| Finalize HealthSource PRD | In Progress |  | 2025-10-10 | Jim / John
| Finalize HealthSource Tech Spec | In Progress |  | 2025-10-24 | John
| Resource/Roadmapping Commitment with Athena | Not Started |  | 2025-10-09 | Bryanna / Leon
| Build - Req API | In Progress |  | 2025-12-01 |  | 2-3 Sprints, expected to be done by mid-Nov
| Build - HS | Not Started |  | 2025-12-01
| Internal Testing of ReqAPI, HS, and STORK | Not Started |  | 2025-12-15 | Steve, John
| PenTesting | Not Started |  | 2025-12-19 | Tyler
| Begin testing with Athena in non-prod | Not Started |  | 2025-01-05 | Steve
| End to End Testing in Prod | Not Started |  | 2025-01-15
| Ops Validation - Request in HS as Expected | Not Started |  | 2025-01-16
| End to End Post Testing Refinement | Not Started |  | 2025-01-30
| Launch in Production Request Intake Between AOne and Datavant HS | Not Started |  | 2025-02-15
Digital Fulfillment | Write PRD for Digital Fulfillment of COC and PAT | Completed | Page: Athena Digital Fulfillment (RTD) | 2025-07-16 | Jenny
| Sandbox access with a mutual customer | Blocked
| Production access with a mutual customer | In Progress | Major blocker - need Athena to push on this with us. Working with OPs to push their customers (CHS, VillageMD, Hugston Clinic). Mitigiating by primarily using FHIR endpoints | 2025-10-15 | Jenny
| Launch Digital Fulfillment for Provider and Patient Use Case in Production | In Progress | Completed some PoC testing with Village MD, Ascension, Hugston Clinic | 2025-11-10 | Jenny | Record Types for Athena
| 2-3 Mutual Customers live on Digital | Not Started
| Testing/Refinement | Not Started
| Launch Digital Fulfillment for Other Use Cases | Not Started | Should be short follow with provider/patient use cases | 2025-12-30 | Jenny
| 5 Mutual Customers live on Digital | Not Started |  | 2025-02-28
Thrive | High level overview (or Workflow) ready for Thrive (Phase 2 In App Experience) | In Progress |  | 2025-10-29 | Bryanna
MSA Signed
| Logistics, coordination, etc of Thrive |  |  |  | Britt L, Maria | Folder, Thrive Project Plan
| Thrive presentation by Kyle | Not Started
Customer Engagement | Athena-led outreach to mutual customers | Not Started
| Athena-led outreach to non-mutual customers | Not Started
| Finalize list of confirmed mutual and non-mutual customers for Phase 1 | Not Started

## Phase 2
See EHR Integrated Experience Planning for up to date version
Stage | Start Date | End Date | Deliverable | Status | Owner | Link
Discovery | 2025-11-01 |  | PRD | In Progress
| 2025-11-17 | 2025-12-06 | Finalize Tech Spec & Create JIRA artifacts | In Progress
| 2025-12-01 |  | Coordinate security review | Not Started
| 2025-12-16 | 2026-01-16 | Align on HS API Requirements | Not Started
Implementation | 2025-12-09 | 2026-01-02 | Create Project Skeleton & Setup Infra | Not Started
| 2026-01-05 | 2026-01-30 | Create EHR Authentication | Not Started
| 2026-01-18 | 2026-02-13 | Implement UI and BFF mock APIs | Not Started
| 2026-02-02 | 2026-02-27 | Build the BFF Routes | Not Started
| 2026-02-15 | 2026-03-13 | Athena alerting | Not Started
Testing/Deployment | 2026-03-02 | 2026-03-27 | Pentesting | Not Started
| 2026-03-02 | 2026-03-27 | Production Deployment & Observability | Not Started
Earlier version
Discovery |  | 2025-11-14 | Complete PRD | In Progress
|  | 2025-11-21 | Finalize Tech Spec and create JIRA artifacts | In Progress
|  | 2025-11-26 | Review Implementation Plan with Internal Stakeholders (HS, ReqAPI, etc) | Not Started
|  | 2025-11-26 | Start Security Review | Not Started
|  | 2025-12-04 | Review Implementation Plan with Athena | Not Started
|  | 2026-12-11 | Idenitfy Pilot Provider + Users | Not Started
Implementation |  | 2025-12-19 | Build Part 1 - Build UI Components | Not Started
|  | 2026-01-30 | Build Part 2 - Build Backend Components | Not Started
|  | 2026-02-13 | Build Part 3 - Connect UI and Backend Components | Not Started
|  | 2026-02-27 | Enable embedding of application into Athena platform | Not Started
Testing |  | 2026-02-20 | Complete Internal Testing | Not Started
|  | 2026-02-27 | Complete Pentesting | Not Started
|  | 2026-03-13 | Complete External Testing with Athena | Not Started
Deployment |  | TBD | TBD | Not Started
|  | TBD | TBD | Not Started
|  | TBD | TBD | Not Started